## Sheet1
Task No | Task Name | Start Week | Finish Week | Week 1 | Week 3 | Week 6 | Week 10 | Week 25 | Week 35 | Week 40 | Week 50 | Week 65 | Week 70 | Week 80 | Week 100 | Week 115 | Week 125 | Week 130
1 | Feasibility Study | Week 1 | Week 3
2 | Defining Buiness Objectives | Week 3 | Week 6
3 | Defining Requirements | Week 6 | Week 10
4 | Effort Estimation | Week 6 | Week 25
5 | Strategic Planning | Week 25 | Week 35
6 | Analyzing Historical Data | Week 35 | Week 40
7 | Analyzing Complexity | Week 40 | Week 50
8 | Analyzing All Risks | Week 40 | Week 50
9 | Budget Estimation | Week 50 | Week 65
10 | Allocating resource | Week 65 | Week 70
11 | Prototyping | Week 70 | Week 80
12 | Coding | Week 80 | Week 100
13 | Software Testing | Week 100 | Week 115
14 | Installation | Week 115 | Week 125
15 | Client Training | Week 125 | Week 130

## Sheet2
Task No | Task Name | Start Date | Finish Date | Task Duration (Days)
1 | Preliminary Project Plan | 2021-03-15 |  | 1
2 | Requirements and Specification analysis | 2021-04-01 | 2021-04-20 | 12
3 | Software Model (UML Diagrams) | 2021-04-21 | 2021-05-20 | 17
4 | Analysis of technical requirements | 2021-05-21 | 2021-07-31 | 40
5 | Module Development | 2021-08-01 | 2021-10-30 | 53
6 | System Integration and Test | 2021-11-01 | 2021-12-30 | 35
7 | Final Product | 2021-12-31 |  | 1
44270
44561